## Sheet1
Week | Phase | Tasks
Week 1 | Requirement Analysis & Design | Identify source database schema, Define AWS S3 structure
Week 2 | Requirement Analysis & Design | Design REST API endpoints, Create high-level architectural diagram
Week 3 | Development & Implementation | Develop Spring Boot microservice, Read images from Oracle DB
Week 4 | Development & Implementation | Upload images to AWS S3, Store metadata and S3 URL
Week 5 | Development & Implementation | Implement CRUD APIs, Integrate security mechanisms (IAM roles, encryption)
Week 6 | Testing & Validation | Unit testing, Performance testing, Integration testing
Week 7 | Deployment & Monitoring | Deploy microservice to staging, Migrate test dataset
Week 8 | Deployment & Monitoring | Go-live with phased migration, Monitor logs and AWS CloudWatch